## Overview
PN site module plan
A public-safe delivery plan for improving navigation, storytelling, privacy, and launch quality.
Plan summary | Value | Current focus | Outcome | Owner | Finish | Evidence
Plan start | 2026-09-13 16:00 | Module 01 | Make the site understandable in one glance | Codex | 2026-09-14 16:00 | /modules/ page + Home link
Modules | 9 | Workbook | One schedule with dates, dependencies, and acceptance checks | Codex | 2026-09-13 16:00 | PN-Site-Module-Timeline.xlsx
Complete | 1 | Source review | Separate personal-site facts from unrelated business material | Codex | 2026-09-13 16:00 | Sources and decision log
In progress | 1
Blocked | 2 | How to use this plan | Update the Status column in Module Timeline and Task Detail. The Overview recalculates automatically.
Not started | 5
Module completion | 11.11%
Calendar days | 35

## Module Timeline
Module timeline
Each site section is treated as a module with one user outcome, one owner, and a measurable finish line.
ID | Module | User outcome | Start | Finish | Days | Priority | Status | Owner | Depends on | Primary deliverable | 2026-09-14 16:00 | 2026-09-21 16:00 | 2026-09-28 16:00 | 2026-10-05 16:00 | 2026-10-12 16:00 | 2026-10-19 16:00
M00 | Discovery and boundaries | Ground the experience in current code and trusted facts without exposing private material. | 2026-09-13 16:00 | 2026-09-13 16:00 | 1 | High | Complete | Codex | None | Reviewed source map
M01 | Wayfinding and module map | A first-time visitor can understand the site and choose a destination in under 20 seconds. | 2026-09-13 16:00 | 2026-09-14 16:00 | 2 | High | In progress | Codex | M00 | /modules/ + Home module link | bar: 2026-09-14 16:00
M02 | Home orientation | Home leads with identity, proof, and three clear next actions instead of a dense tool console. | 2026-09-14 16:00 | 2026-09-16 16:00 | 3 | High | Not started | Pierson + Codex | M01 | Revised Home hierarchy | bar: 2026-09-14 16:00
M03 | Experience timeline | Recruiters can scan years, outcomes, and transferable skills without opening every detail panel. | 2026-09-17 16:00 | 2026-09-19 16:00 | 3 | High | Not started | Pierson + Codex | M02 | Year jump navigation + copy cleanup | bar: 2026-09-14 16:00
M04 | Public proof pages | About, Projects, Contact, and Tools become real destinations with confirmed claims only. | 2026-09-20 16:00 | 2026-09-26 16:00 | 7 | High | Blocked | Pierson + Codex | M03; content decisions | Four public pages | bar: 2026-09-14 16:00 to 2026-09-21 16:00
M05 | Knowledge system | Atlas, Backstage, and Notes explain their relationship and privacy state consistently. | 2026-09-27 16:00 | 2026-10-02 16:00 | 6 | Medium | Not started | Codex | M01 | Shared orientation copy | bar: 2026-09-21 16:00 to 2026-09-28 16:00
M06 | Portfolio and privacy | The tracker communicates freshness, visibility, and limits before revealing any figures. | 2026-10-03 16:00 | 2026-10-09 16:00 | 7 | High | Blocked | Pierson + Codex | Privacy choice; secret setup | Hardened tracker flow | bar: 2026-09-28 16:00 to 2026-10-05 16:00
M07 | Discoverability and quality | Every public module is fast, accessible, link-safe, and accurately described to search and AI systems. | 2026-10-10 16:00 | 2026-10-13 16:00 | 4 | High | Not started | Codex | M02-M06 | QA report + crawl kit | bar: 2026-10-05 16:00 to 2026-10-12 16:00
M08 | Launch and cadence | The site has a repeatable release checklist, update owner, and monthly maintenance rhythm. | 2026-10-14 16:00 | 2026-10-17 16:00 | 4 | Medium | Not started | Pierson + Codex | M07 | Launch checklist | bar: 2026-10-12 16:00

## Task Detail
Task detail
The working checklist behind each module. Status is editable; acceptance evidence defines done.
Module | Task | Outcome | Owner | Start | Finish | Status | Dependency | Acceptance evidence | Site path
M00 | Inventory public routes and test coverage | No existing feature is accidentally replaced | Codex | 2026-09-13 16:00 | 2026-09-13 16:00 | Complete | None | Route map and baseline tests recorded | Repository
M00 | Review both Google Drive contexts | Relevant portfolio facts are grounded; unrelated service-site material is separated | Codex | 2026-09-13 16:00 | 2026-09-13 16:00 | Complete | Drive access | Source log distinguishes personal and school contexts | Private source review
M00 | Review Word and OneDrive material | Legacy résumé and SEO drafts inform decisions without becoming public copy | Codex | 2026-09-13 16:00 | 2026-09-13 16:00 | Complete | OneDrive access | Excluded claims and legacy language are documented | Private source review
M01 | Create a module index | Visitors see the purpose and privacy state of every live section | Codex | 2026-09-13 16:00 | 2026-09-14 16:00 | In progress | M00 | Seven module cards, working links, semantic headings | /modules/
M01 | Replace the Home coming-soon strip | No vague or dead destinations remain on Home | Codex | 2026-09-13 16:00 | 2026-09-14 16:00 | In progress | Module index | Home links to the module map and timeline workbook | /
M01 | Link the plan workbook | The schedule is downloadable from the module index | Codex | 2026-09-13 16:00 | 2026-09-13 16:00 | In progress | Workbook export | Workbook link returns the expected xlsx file | /assets/planning/
M02 | Reduce competing Home actions | Identity, experience, and module exploration lead the first viewport | Codex | 2026-09-14 16:00 | 2026-09-15 16:00 | Not started | M01 | Three primary paths; no duplicate calls to action | /
M02 | Rewrite current-state labels from a dated source | Public status stays concrete and maintainable | Pierson + Codex | 2026-09-15 16:00 | 2026-09-16 16:00 | Not started | Pierson confirmation | Every status has a source date and owner | /
M03 | Add year jump links | Visitors can move directly to 2026, 2025, 2024, or 2023 | Codex | 2026-09-17 16:00 | 2026-09-17 16:00 | Not started | M02 | Keyboard-accessible links land below sticky controls | /experience/
M03 | Resolve public open-question boxes | The timeline contains confirmed claims, not editorial notes | Pierson | 2026-09-17 16:00 | 2026-09-18 16:00 | Blocked | Decision D01-D05 | No public box is labelled Open - Pierson | /experience/
M03 | Tighten the 2024 and 2025 scan path | Thin years read intentionally rather than unfinished | Pierson + Codex | 2026-09-18 16:00 | 2026-09-19 16:00 | Blocked | Pierson facts | Each retained year has one verified anchor | /experience/
M04 | Build About from confirmed paragraphs | A reader understands the through-line in under two minutes | Codex | 2026-09-20 16:00 | 2026-09-21 16:00 | Blocked | D01; D05 | One H1, 250-350 words, no placeholders | /about/
M04 | Build Projects as proof cards | Work examples show problem, action, and outcome | Codex | 2026-09-22 16:00 | 2026-09-23 16:00 | Blocked | D02-D04 | Four confirmed projects with valid destinations | /projects/
M04 | Build Tools hub | Public and private tools have clear access and data boundaries | Codex | 2026-09-24 16:00 | 2026-09-24 16:00 | Not started | M06 wording | Tracker card states visibility and freshness | /tools/
M04 | Build Contact without a form | Visitors can choose email, LinkedIn, or GitHub without a broken workflow | Pierson + Codex | 2026-09-25 16:00 | 2026-09-26 16:00 | Blocked | D06-D07 | Every public contact link is confirmed and works | /contact/
M05 | Add shared orientation copy | Atlas, Backstage, and Notes answer what, why, and privacy state consistently | Codex | 2026-09-27 16:00 | 2026-09-29 16:00 | Not started | M01 | Same three-field pattern appears on all three modules | Knowledge modules
M05 | Test mobile compositions | Bottle, stars, vault, and studio remain legible in portrait | Codex | 2026-09-30 16:00 | 2026-10-02 16:00 | Not started | Orientation copy | 375px and 768px screenshots show no clipping | Knowledge modules
M06 | Put privacy state before portfolio data | Visitors know whether figures are public, obscured, or private before interaction | Codex | 2026-10-03 16:00 | 2026-10-05 16:00 | Blocked | D08 | Visibility statement precedes all holdings UI | /tools/tracker/
M06 | Reconcile monthly-tab naming | New tabs appear without hardcoded month names | Codex | 2026-10-06 16:00 | 2026-10-07 16:00 | Not started | Sheet read access | August and Early September both parse into five platform sections | Tracker build
M06 | Add freshness and error states | Stale data is obvious and never presented as live | Codex | 2026-10-08 16:00 | 2026-10-09 16:00 | Not started | Monthly parser | Empty, stale, and fetch-failure paths are tested | /tools/tracker/
M07 | Run link, heading, and console checks | Broken navigation and invalid structure are caught before release | Codex | 2026-10-10 16:00 | 2026-10-10 16:00 | Not started | M02-M06 | All internal links resolve; one H1 per page; no console errors | All public routes
M07 | Finish social-preview metadata | Shared links have a deliberate image and accurate description | Pierson + Codex | 2026-10-11 16:00 | 2026-10-12 16:00 | Blocked | D09 | Open Graph image is raster, sized, and reachable | Head metadata
M07 | Run mobile and reduced-motion review | Core content works at 360px and without animation | Codex | 2026-10-12 16:00 | 2026-10-13 16:00 | Not started | All modules | No sideways scroll; focus visible; reduced-motion path verified | All public routes
M08 | Create release checklist | Every launch uses the same evidence gate | Codex | 2026-10-14 16:00 | 2026-10-15 16:00 | Not started | M07 | Checklist includes privacy grep, tests, links, mobile, metadata | Repository docs
M08 | Assign monthly upkeep | Each dynamic source has an owner and refresh trigger | Pierson | 2026-10-16 16:00 | 2026-10-17 16:00 | Not started | Release checklist | Owner and cadence exist for tracker, timeline, résumé, and crawl kit | Maintenance plan

## Decisions
Decisions needed
Only Pierson can close these content and privacy choices. Recommended defaults keep the site accurate until then.
ID | Decision | Why it matters | Recommended default | Needed before | State | Evidence to add
D01 | AI Club title and term | Current pages say incoming president without exact dates | Use member/leadership-neutral wording until confirmed | M02-M04 | Open | Exact title and start/end dates
D02 | True North legal/public name | Source documents use multiple company names | Keep True North Services LLC only where filing is confirmed | M03-M04 | Open | Preferred public name and filing name
D03 | Oasis to True North relationship | The experience story changes if it was a rebrand versus a new company | Describe as two chapters; do not claim a formal rebrand | M03-M04 | Open | One-sentence relationship
D04 | Student Maintenance entry | Role, dates, and equity description are not confirmed for public use | Omit from new pages until confirmed | M03-M04 | Open | Public role wording and dates
D05 | 2027 direction | About needs a closing point of view | End with current work instead of predicting a job target | M04 | Open | One sentence on post-graduation direction
D06 | Public contact email | The current Gmail address may not be the final professional address | Keep the current address until a replacement exists | M04 | Open | Confirmed public email
D07 | GitHub profile URL | The public contact page needs a working destination | Omit GitHub until the username is confirmed | M04 | Open | Exact profile URL
D08 | Tracker visibility model | Portfolio numbers are personal financial data | Keep read-only, visibly labeled, and censored by default | M06 | Open | Public vs gated vs local-only choice
D09 | Social share image | Open Graph metadata has no raster preview | Use a simple branded PN card with no personal photo | M07 | Open | Approved PNG or approved design direction

## Sources
Source map
Private sources are named only at a safe level. Their file IDs, holdings, credentials, and unpublished notes are intentionally excluded.
Source | Account or location | Visibility | Used for | Included in public plan | Reviewed | Public URL
Current PN website repository | OneDrive synced project | Public code; private folders ignored | Existing routes, design system, tests, roadmap | Yes | 2026-09-13 16:00 | https://piersonnorris.github.io/
Blueprint, content, and roadmap | PN website project docs | Public-safe repository docs | Confirmed claims, architecture, open decisions | Yes | 2026-09-13 16:00 | https://piersonnorris.github.io/vault/
Asset Tracking build specification | Personal Google Drive | Private | Portfolio schema, five platforms, privacy choices | Structure only | 2026-09-13 16:00
Asset Tracking workbook | School Google Drive connection | Private financial data | Tab names and parser compatibility | Counts and structure only | 2026-09-13 16:00
Website Specifications | School Google Drive connection | Separate service-business context | Separation check; not a PN personal-site source | No | 2026-09-13 16:00
Legacy résumé | Personal OneDrive Word file | Private source | Early work-history cross-check | Confirmed facts only | 2026-09-13 16:00
Legacy service-site SEO draft | Personal OneDrive Word file | Private legacy draft | Language-quality warning; excluded from PN copy | No | 2026-09-13 16:00
School OneDrive browser session | Elon Microsoft account | Session unavailable | No material used | No | 2026-09-13 16:00